## Sheet1
Risk ID | Risk Description | Likelihood | Impact | Inherent Risk | Control | Residual Risk | Remediation | Owner | Risk Status
R-001 | MFA only applies to admin users | Medium | High | High | Admin MFA enabled | Medium | Enforce MFA for all users | IT Security Team | Open
R-002 | Privileged accounts not reviewed regularly | High | High | High | Manual admin oversight | Medium | Implement quarterly priveleged access reviews | Identity & Access Management | Open
R-003 | Log retention period insufficient | Medium | Medium | Medium | Basic logging enabled | Medium | Increase log retention to 90+ days. | Security Operations | Open
R-004 | Quarterly vulnerability scans only | Medium | High | High | Quarterly scanning process | Medium | Conduct monthly vulnerability scans | Vulnerability Management Team | Open
R-005 | No formal critical patch management SLA | High | High | High | Informal patching process | High | Implement patch management timelines. | IT Operations | Open
R-006 | No annual incident response tabletop exercises | Medium | Medium | Medium | Incident response policy exists | Medium | Conduct annual tabletop exercises. | Security Operations | Planned
R-007 | Weak subcontractor oversight | High | High | High | Partial subcontractor review | High | Require formal fourth-party risk management. | Vendor Risk Management | Open
R-008 | Limited suspicious login monitoring | Medium | High | High | Basic login logging enabled | Medium | Implemented automated login alerting. | Security Operations | Open
R-009 | Inconsistent backup recovery testing | Medium | High | High | Backup encryption enabled | Medium | Perform quarterly backup recovery testing. | Infrastructure Team | Planned
R-010 | Partial HIPAA compliance alignment | High | High | High | Basic compliance controls implemented | High | Conduct HIPAA compliance gap assessment. | Compliance Team | Open
R-011 | Endpoint detection tools not fully deployed | Medium | High | High | Limited endpoint monitoring | Medium | Deploy endpoint detection and response tools. | Endpoint Security Team | Open
R-012 | Sensitive data classification inconsistent | Medium | Medium | Medium | Partial data classification process | Medium | Standardize data classification procedures. | Data Governance Team | Planned